PRODUCT ROADMAP & RELEASE PLAN

Wave Projects Center.ID

DOCUMENT INFORMATION

| Item | Value |
| --- | --- |
| Document Name | Product Roadmap & Release Plan |
| Product | Wave Projects Center.ID |
| Version | 1.0 |
| Status | Approved |
| Product Owner | Ariyas Pratama Ramadhan |
| Development Methodology | Agile Scrum |
| Sprint Duration | 2 Weeks |
| Planning Horizon | 24 Months |
| Initial Release Target | Q3 2026 |

1. DOCUMENT PURPOSE

Dokumen ini mendefinisikan arah pengembangan produk Wave Projects Center.ID secara bertahap mulai dari MVP hingga menjadi platform SaaS berskala besar.

Tujuan utama:

- Menentukan prioritas bisnis.

- Menentukan urutan pengembangan.

- Mengontrol risiko pengembangan.

- Menentukan target setiap release.

- Menjadi dasar evaluasi kemajuan proyek.

2. PRODUCT VISION

Wave Projects Center.ID akan menjadi platform terintegrasi yang menghubungkan:

- Klien

- AI Consultant

- Marketing Team

- Developer Team

- Payment System

- Project Delivery

ke dalam satu ekosistem digital.

Target akhir:

Menjadi platform otomatisasi pemesanan jasa pembuatan software berbasis AI yang mampu menangani banyak proyek secara paralel dengan biaya operasional minimal.

- STRATEGIC OBJECTIVES

Tahun Pertama

Fokus:

Membuat sistem stabil dan menghasilkan transaksi.

Target:

- MVP Release

- 100+ pelanggan

- 50+ proyek berhasil

- 99.9% uptime

Tahun Kedua

Fokus:

Skalabilitas dan otomatisasi.

Target:

- SaaS Ready

- Multi-Tenant

- Auto Team Assignment

- AI Project Estimation

Tahun Ketiga

Fokus:

Ekspansi bisnis.

Target:

- White Label Platform

- Mobile Application

- Enterprise Package

- PRODUCT EVOLUTION ROADMAP

PHASE 1

MVP FOUNDATION

Periode: Q3 2026

Target:

Membuktikan model bisnis.

Fitur:

✓ Landing Website

✓ Portfolio

✓ Package Management

✓ Authentication

✓ AI Consultation

✓ Checkout

✓ Midtrans Integration

✓ Cloudinary Integration

✓ AI PRD Generator

✓ Developer Dashboard

✓ Notification Center

Success Metric:

- 10 transaksi pertama

- 95% checkout berhasil

- Error rate < 1%

Release:

- v1.0.0

PHASE 2

OPERATIONAL AUTOMATION

Periode: Q4 2026

Target:

Mengurangi pekerjaan manual.

Fitur:

✓ Advanced Dashboard

✓ Revenue Analytics

✓ Project Timeline

✓ Customer Tracking

✓ Invoice Generator

✓ E-Sign BAST

✓ Activity Logs

✓ Audit Logs

✓ SLA Monitoring

Success Metric:

- 70% proses otomatis

- Waktu administrasi turun 50%

Release:

- v1.5.0

PHASE 3

INTELLIGENT WORKFLOW

Periode: Q1 2027

Target:

Mengoptimalkan distribusi pekerjaan.

Fitur:

✓ Smart Routing

✓ AI Project Complexity Analysis

✓ AI Cost Prediction

✓ AI Team Assignment

✓ AI Workload Monitoring

✓ AI Risk Detection

Success Metric:

- Distribusi tugas otomatis

- Utilisasi tim > 80%

Release:

- v2.0.0

PHASE 4

MULTI TENANT SAAS

Periode: Q2 2027

Target:

Platform dapat disewakan.

Fitur:

✓ Multi Tenant Architecture

✓ Tenant Billing

✓ Tenant Isolation

✓ Tenant Branding

✓ Tenant Dashboard

✓ Subscription Management

Success Metric:

- 10 tenant aktif

- MRR positif

Release:

- v3.0.0

PHASE 5

MOBILE PLATFORM

Periode: Q3 2027

Target:

Memperluas akses pengguna.

Fitur:

✓ Android App

✓ PWA Enhancement

✓ Push Notification Mobile

✓ Mobile Tracking

✓ Mobile Delivery

Release:

- v4.0.0

5. RELEASE CALENDAR

Q3 2026

Release 1.0.0

MVP

Target Go Live:
September 2026

Q4 2026

Release 1.5.0

Operations Automation

Target Go Live:
Desember 2026

Q1 2027

Release 2.0.0

AI Workflow

Target Go Live:
Maret 2027

Q2 2027

Release 3.0.0

SaaS Platform

Target Go Live:
Juni 2027

Q3 2027

Release 4.0.0

Mobile Platform

Target Go Live:
September 2027

6. MVP RELEASE PLAN

Release Name:

Wave Projects Center.ID v1.0

Target Date:

September 2026

Scope:

EPIC-01 Landing Website

EPIC-02 Authentication

EPIC-03 AI Consultation

EPIC-04 Package Management

EPIC-05 Checkout

EPIC-06 Midtrans

EPIC-07 Cloudinary

EPIC-08 AI PRD Generator

EPIC-09 Dashboard

EPIC-10 Notification

Excluded:

Multi Tenant

Mobile App

Advanced Analytics

Smart Routing

AI Team Assignment

7. SPRINT RELEASE PLAN

Sprint Duration:

14 Days

Sprint 1

Infrastructure Foundation

Deliverables:

- Git Repository

- Laravel Setup

- TiDB Setup

- Vercel Setup

- Cloudinary Setup

Milestone:

- Development Environment Ready

Sprint 2

Landing Website

Deliverables:

- Landing Page

- Portfolio

- Pricing

Milestone:

- Marketing Website Ready

Sprint 3

Authentication

Deliverables:

- Login

- Logout

- Role Management

Milestone:

- User Management Ready

Sprint 4

AI Consultation

Deliverables:

- Gemini Integration

- Chat Interface

- Package Recommendation

Milestone:

- AI Consultation Ready

Sprint 5

Checkout

Deliverables:

- Order Creation

- Package Selection

- Upload File

Milestone:

- Checkout Ready

Sprint 6

Payment Gateway

Deliverables:

- Midtrans Integration

- Callback Processing

Milestone:

- Payment Ready

Sprint 7

AI PRD Generator

Deliverables:

- Prompt Builder

- Queue Processing

- PRD Generation

Milestone:

- Automation Ready

Sprint 8

Dashboard & Notification

Deliverables:

- Dashboard

- OneSignal

- Analytics Widget

Milestone:

- MVP Complete

8. RESOURCE ALLOCATION PLAN

Product Owner

1 Person

UI/UX Designer

1 Person

Frontend Developer

2 Persons

Backend Developer

2 Persons

QA Engineer

1 Person

DevOps Engineer

1 Person

Total Team:

8 Resources

9. DEPENDENCY MATRIX

Cloudinary

Required Before:

File Upload Module

Midtrans

Required Before:

Payment Module

Gemini API

Required Before:

AI Consultation

AI PRD Generator

OneSignal

Required Before:

Notification Module

TiDB Cloud

Required Before:

All Backend Modules

10. RISK MANAGEMENT

RISK-001

Gemini API Rate Limit

Probability:
Medium

Impact:
High

Mitigation:

OpenRouter Failover

RISK-002

TiDB Connection Exhaustion

Probability:
Medium

Impact:
High

Mitigation:

Connection Pooling

RISK-003

Vercel Timeout

Probability:
High

Impact:
High

Mitigation:

Asynchronous Queue

RISK-004

Payment Failure

Probability:
Low

Impact:
High

Mitigation:

Webhook Retry

Idempotency Layer

11. RELEASE GOVERNANCE

Release Manager

Product Owner

Release Approval

Lead Developer

QA Lead

Product Owner

Release Requirements

✓ All Critical Bugs Closed

✓ UAT Passed

✓ Load Test Passed

✓ Security Review Passed

✓ Backup Verified

✓ Rollback Tested

12. GO LIVE CRITERIA

System Availability

≥ 99.9%

API Response Time

≤ 2500 ms

Error Rate

≤ 1%

Checkout Success Rate

≥ 95%

Payment Success Rate

≥ 98%

UAT Pass Rate

100%

DOCUMENT APPROVAL

Prepared By : Ariyas Pratama Ramadhan

Reviewed By :Ariyas Pratama Ramadhan

Approved By : Ariyas Pratama Ramadhan

Version : 1.0